## Summary
Project Plan Summary
# | Milestone | Start Date | End Date | Calendar Days
A | Preliminary Activities | 2024-09-23 | 2024-10-04 | 12
B | Blue Print Sign-Off | 2024-10-04 | 2024-11-13 | 41
C | SAP Web Service Development | 2024-10-03 | 2024-11-14 | 43
D | Pre-Requisites | 2024-11-15 | 2024-12-06 | 22
E | NS2P Configuration | 2024-11-14 | 2024-12-19 | 36
F | Unit Testing | 2024-12-20 | 2025-01-22 | 34
G | User Acceptance Testing | 2025-01-23 | 2025-02-13 | 22
H | Go-Live | 2025-02-14 | 2025-02-25 | 12

## PO Material
| NimbleS2P | [8 empty] | Project start: | [7 empty] | 2024-09-23
| JNIL | Leg 1 : PO Material | [7 empty] | Display week: | [7 empty] | 1
[10 empty] | 2024-09-23 | [6 empty] | 2024-09-30 | [6 empty] | 2024-10-07 | [6 empty] | 2024-10-14 | [6 empty] | 2024-10-21 | [6 empty] | 2024-10-28 | [6 empty] | 2024-11-04 | [6 empty] | 2024-11-11 | [6 empty] | 2024-11-18 | [6 empty] | 2024-11-25 | [6 empty] | 2024-12-02 | [6 empty] | 2024-12-09 | [6 empty] | 2024-12-16 | [6 empty] | 2024-12-23
ID | ID | TASK | Dependency | ASSIGNED TO | PROGRESS | Days | START | END | time axis 2024-09-23 to 2024-12-29
 | time axis 2024-09-23 to 2024-12-29
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
| A | Preliminary Activities
| 1 | Onsite Visit - Project Commencement Meeting |  | Joint | 100% | 6 | 2024-09-23 | 2024-09-28 | 6
| 2 | Indicative Project Plan |  | NS2P | 100% | 4 | 2024-09-30 | 2024-10-03 | 4
| 3 | Project Plan Review |  | NS2P | 100% | 1 | 2024-10-04 | 2024-10-04 | 1
| B | Blue Print Sign-Off
| 4 | BBP Document Preparation - Draft 1 (Scanning after UD) |  | NS2P | 100% | 7 | 2024-10-04 | 2024-10-10 | 7
| 5 | BBP Document Preparation - Draft 2 (Scanning at the Gate) |  | NS2P | 100% | 1 | 2024-10-18 | 2024-10-18
| 6 | BBP Review 1 |  | Joint | 0% | 1 | 2024-10-25 | 2024-10-25 | 1
| 7 | BBP Update as per Review 1 |  | NS2P | 0% | 3 | 2024-10-28 | 2024-10-30 | 3
| 8 | BBP Review 2 + Technical Review |  | Joint | 0% | 1 | 2024-11-04 | 2024-11-04 | 1
| 9 | BBP final update as per Review 2 and Release |  | NS2P | 0% | 2 | 2024-11-05 | 2024-11-06 | 2
| 12 | Prerequisites Document - SAP APIs & Web Services, Scanner Procurement, Bar Code Printer and Bar Code Readers, Other Static Masters, etc, User Assignment Logic or formula for calculative fields |  | NS2P | 0% | 1 | 2024-11-07 | 2024-11-07 | 1
| 13 | BBP Sign off |  | Joint | 0% | 6 | 2024-11-08 | 2024-11-13 | 6
| C | SAP Web Service Development
| 14 | API Structure Documentation |  | NS2P | 100% | 5 | 2024-10-03 | 2024-10-07 | 5
| 15 | Review Meeting with Mahesh Kalkar |  | NS2P | 100% | 1 | 2024-10-08 | 2024-10-08 | 1
| 15 | Masters API - Tax Master, Withhold Tax Master, Cost Centre Master, GL Master, Currency Master |  | NECO | 0% | 4 | 2024-10-08 | 2024-10-11 | 4
| 16 | PO API {Sync for Create + Update} AND {OnDemand} - This Header + Line Items |  | NECO | 0% | 4 | 2024-10-08 | 2024-10-11 | 4
| 17 | Vendor API {Sync for Create + Update} AND {OnDemand} |  | NECO | 0% | 3 | 2024-10-14 | 2024-10-16 | 3
| 18 | GRN Sync API {Create + Update} |  | NECO | 0% | 3 | 2024-10-17 | 2024-10-19 | 3
| 19 | Foreign Currency Exchange Rate API {On-Demand} |  | NECO | 0% | 3 | 2024-10-21 | 2024-10-23 | 3
| 20 | Wayment Bridge API |  | NECO | 0% | 3 | 2024-10-17 | 2024-10-19 | 3
| 20 | Lab Report API |  | NECO | 0% | 3 | 2024-10-20 | 2024-10-22 | 3
| 20 | LD & Open Advances Pull {On-Demand} |  | NECO | 0% | 3 | 2024-10-24 | 2024-10-26 | 3
| 21 | Invoice Parking |  | NECO | 0% | 3 | 2024-10-28 | 2024-10-30 | 3
| 22 | Invoice Posting |  | NECO | 0% | 3 | 2024-11-01 | 2024-11-03 | 3
| 23 | LD Posting |  | NECO | 0% | 3 | 2024-11-01 | 2024-11-03 | 3
| 24 | Debit Note Posting |  | NECO | 0% | 3 | 2024-11-05 | 2024-11-07 | 3
| 25 | Retention Posting |  | NECO | 0% | 3 | 2024-11-09 | 2024-11-11 | 3
| 26 | Payment Status |  | NECO | 0% | 3 | 2024-11-12 | 2024-11-14 | 3
| D | Pre-Requisites
| 27 | Rejection Reason Masters at Finance Level and Respective Action |  | NECO | 0% | 4 | 2024-11-15 | 2024-11-18 | 4
| 28 | Rejection Reason Masters at Internal Audit and Respective Action |  | NECO | 0% | 4 | 2024-11-20 | 2024-11-23 | 4
| 29 | User Assignment Logic for Finance & Internal Audit based on Vendor Code |  | NECO | 0% | 4 | 2024-11-26 | 2024-11-29 | 4
| 30 | Scanner & Barcode Printer Procurement & Installation |  | NECO | 0% | 3 | 2024-11-25 | 2024-11-27 | 3
| 31 | Barcode Testing with NimbleS2P |  | Joint | 0% | 5 | 2024-12-02 | 2024-12-06 | 5
| E | NS2P Configuration
| 32 | Repository Creation & Master Table Configuration |  | NS2P | 0% | 1 | 2024-11-14 | 2024-11-14 | 1
| 33 | Invoice Processing Forms Field Configuration (Initiator Form) |  | NS2P | 0% | 5 | 2024-11-15 | 2024-11-19 | 5
| 34 | Build & Show(Forms), access to be given to NECO users for Forms Review |  | Joint | 0% | 1 | 2024-11-20 | 2024-11-20 | 1
| 35 | Field Validations, Formulas and SAP Integration (dependent on SAP APIs) |  | NS2P | 0% | 10 | 2024-11-21 | 2024-11-30 | 10
| 36 | Form Changes based on Review |  | NS2P | 0% | 3 | 2024-12-02 | 2024-12-04 | 3
| 37 | SAP Web services Integration |  | NS2P | 0% | 6 | 2024-12-02 | 2024-12-07 | 6
| 38 | Workflow Configuration I (Raw) |  | NS2P | 0% | 6 | 2024-12-09 | 2024-12-14 | 6
| 39 | Workflow Configuration II(Stores) |  | NS2P | 0% | 3 | 2024-12-17 | 2024-12-19 | 3
| F | Unit Testing
| 40 | Test Cases from Neco with data in SAP DEV environment |  | NECO | 0% | 15 | 2024-11-21 | 2024-12-05 | 15
| 41 | Test Cases execution by NS2P Team in DEV environment |  | NS2P | 0% | 7 | 2024-12-20 | 2024-12-26 | 7
| 42 | PO Material - Walkthrough#1 |  | Joint | 0% | 1 | 2024-12-27 | 2024-12-27 | 1
| 43 | Feedback#1 from Neco |  | NECO | 0% | 1 | 2024-12-30 | 2024-12-30 | 1
| 44 | Fixes on Feedback#1 |  | NS2P | 0% | 2 | 2025-01-02 | 2025-01-03 | 2
| 45 | PO Material - Walkthrough#2 |  | Joint | 0% | 1 | 2025-01-06 | 2025-01-06 | 1
| 46 | Feedback#2 from Neco |  | NECO | 0% | 1 | 2025-01-08 | 2025-01-08 | 1
| 47 | Fixes on Feedback#2 |  | NS2P | 0% | 6 | 2025-01-09 | 2025-01-14 | 6
| 48 | User Manual Preparation (Scanner, SSC - Finance, Supplier) |  | NS2P | 0% | 3 | 2025-01-15 | 2025-01-17 | 3
| 49 | QA Migration Activities |  | NS2P | 0% | 2 | 2025-01-20 | 2025-01-21 | 2
| 50 | SAP Web services, Static Masters, etc to be completed (QA instance) |  | NECO | 0% | 27 | 2024-12-05 | 2024-12-31 | 27
| 51 | API URLs Reconfiguration & Testing |  | NS2P | 0% | 1 | 2025-01-22 | 2025-01-22 | 1
| G | User Acceptance Testing
| 52 | UAT Training |  | Joint | 0% | 1 | 2025-01-23 | 2025-01-23 | 1
| 53 | UAT Execution |  | Joint | 0% | 7 | 2025-01-24 | 2025-01-30 | 7
| 54 | Feedback#3 from Neco |  | NECO | 0% | 1 | 2025-01-31 | 2025-01-31 | 1
| 55 | User Manual Feedback |  | NECO | 0% | 1 | 2025-01-31 | 2025-01-31 | 1
| 56 | Fixes on Feedback #3 |  | NS2P | 0% | 4 | 2025-02-03 | 2025-02-06 | 4
| 57 | Final UAT by Neco |  | Joint | 0% | 4 | 2025-02-07 | 2025-02-10 | 4
| 58 | UAT Sign Off |  | NECO | 0% | 1 | 2025-02-13 | 2025-02-13 | 1
| H | Go-Live
| 59 | User Manual Update |  | NS2P | 0% | 1 | 2025-02-14 | 2025-02-14 | 1
| 60 | BBP Revision |  | Joint | 0% | 2 | 2025-02-14 | 2025-02-15 | 2
| 61 | BBP Revision Sign-Off |  | NS2P | 0% | 5 | 2025-02-17 | 2025-02-21 | 5
| 62 | Production Porting |  | Joint | 0% | 3 | 2025-02-22 | 2025-02-24 | 3
| 63 | Go-Live |  | NS2P | 0% | 0 | 2025-02-25 | 2025-02-25 | 1
Insert new rows ABOVE this one
Formulas:
Display week: = [Display week:, row below]

## Holidays List
Holidays List (October 2024 - March 2025)
Name and Description | Date
Mahatma Gandhi Jayanti | 2024-10-02
Vijaya Dashmi | 2014-10-12
Deepavali Amavasya (Laxmi Puja) | 2024-11-01
Deepavali (Balipadyami) | 2024-11-02
Guru Nanak Jayanti | 2024-11-15
Christmas | 2024-12-25
New Year's eve | 2024-12-31
New Year's Day | 2025-01-01
Republic Day | 2025-01-26
Maha Shivaratri | 2025-02-26
Holi | 2025-03-13

## Meeting Logs
Meeting Date | Points Discussed | Done by
2024-10-04 | Project Plan Discussion- PO Material | Sukanta N, Hruday S, Chandresh S, Mahima S, Vanshita L
2024-10-08 | API Document Discussion | Mahesh Kalkar, Shreyas, Vanshita
2024-10-10 | PO Material-Discussion & Demo (HODs)
2024-10-17 | Scanning Process Review (scanning at the gate)